|  |  |  |  |
| --- | --- | --- | --- |
| Email Dara (Kildare County Council) about litter pickers | Ms. Mann  | Friday, 16th of November 2018 | Completed |
| Monitoring & collecting of litter | Siara, Thomas, Kraig & Josh | Daily: From Monday, 26th of November 2018 | Ongoing |
| Experiment with position of yard bins (Centre of yard between grass & tarmac) | Adam | Friday, 16th of November 2018 | Completed |
| Inform Juniors about the new position of yard bins  | Adam & Ryan | Friday, 16th of November 2018 | Completed |
| Inform Juniors about the purpose of the Greens School project and our aim to reduce litter in the school grounds | Green Schools Committee | Friday, 23rd of November 2018 | Completed |
| Senior pupils will help teacher on yard to encourage Juniors tidy away lunch and keep hall area clean.(Amend timetable and give specific days so that pupils in the Senior Class know when they are on. Timetable amended 7/06/19) | Senior Class pupils | Daily: From Friday, 16th of November 2018 | Ongoing |
| Review progress of Litter Plan to date: Conduct a second Litter survey. | Siara, Thomas, Kraig & Josh | Two weeks from the 28th of January 2019 to the 8th of February 2019 | Completed |
| Draw up a ‘Litter Control Policy’ to be ratified by the Board of Management in May 2019. | Green Schools CommitteeMs. MannMs. DunneBoard of Management  | May 2019 | Completed |
| Green Code* Come up with a Green Code/ Slogan to support our school campaign to reduce litter and waste.
* Display the Green Code on Green Schools noticeboard and in other visible areas around the school).
 | Green Schools Committee | June 2019 | Completed(‘Go Green! Go Clean!’) |
| 2019/2020 |
| In September 2019, pupil jobs and responsibilities will have to be revisited. * Litter picking:
* Senior pupils help teacher on yard to encourage Juniors tidy away lunch and keep hall area clean. (New timetable required in September 2019)
 | Green Schools Committee | September 2019 |  |
| Review progress of Litter Plan to date: Conduct a Litter survey. | Adam & Siara | November 2019 | Completed |
| 2020/2021 |
| Daily Litter picking. | Colin & Adam | Daily | Ongoing |
| Review progress of Litter Plan to date: Conduct a Litter survey. | Colin & Adam | 19th October 2020-November 9th of 2020 (10 days in total) | Completed  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |
|  |  |  |  |